## Project Timeline
Grant Submission Timeline
Start Date: | 2019-01-31 |  |  |  |  | Sponsor Due Date: |  | 2019-02-13 | [11 empty] | DEADLINE
| Submit - 3 weeks |  |  |  |  | Submit - 2 weeks |  | Submit - 2 weeks |  |  |  |  | Submit - 1 week |  |  |  |  | Submit week
| jan | jan | jan | jan | jan | jan | jan | jan | jan | jan | jan | feb | feb | feb | feb | feb | feb | feb | feb | feb
| thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed
Assigned to: | 2019-01-17 | 2019-01-18 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-11 | 2019-02-12 | 2019-02-13
PI | 2019-01-17: Request Sub documbents and connect Stephanie with contact at Sub site, this allows Sub to adhere to their institutional grant submission guidelins.
Stephanie | 2019-01-31: Review sub docs
PI | 2019-02-04: Day 1. PI provides OLCS for upload into cherp and Budget/Just for Chief approval, along with the submission of all docs. Days 2-3. Stephanie reviews all documents prior to OSP review.
Stephanie | 2019-02-06: Submit to OSP
OSP | 2019-02-07: OSP Review/Edit period and final Science if necessary
PI/OSP | 2019-02-12: With PI approval OSP submits